## Slide 1: PIAB – Service Delivery
MIX Networks and DataRemote Proprietary and Confidential

## Slide 2: Service Delivery Key Milestones
Start: Order Received
Start: Tech Visit Planned Arrival Time
Start: Ready to Cross-Connect
End: Tech Visit Planned Arrival Time
End: Ready to Cross Connect
End: Install Complete
Customer LCON Coordination
  Identify Alarm Vendor Contact Info
Obtain CSR
  Identify TNs and other CSR details
  Procure pair & binding post info
Porting
  Submit porting requests
Confirm WAN Readiness
  Customer firewall preparation
  Identify custom WAN/LTE configurations
Staging & Kitting
  SIM Activation
  SIP Accounts & VoIP Provisioning
  Device Firmware & Configuration
Prep
  Tech Arrival
  LCON Meetup
  Obtain CPE shipped to site
  Obtain access to facility & workspace
  Request alarm account to test mode
Tag & Trace
  Inventory POTS DIDs
  Confirm analog equipment operation
  Identify lines at DMARC
  Select install location
Install PIAB
  Assemble & Power up PIAB
  Perform connectivity test
  Perform line tests
Voice Line Cross-Connect
  Disconnect POTS – Connect PIAB
  Test voice calls both directions
FAX Line Cross-Connect
  Disconnect POTS – Connect PIAB
  Test FAX calls both directions
Alarm Line Cross-Connect
  Disconnect POTS – wait 60s
  Connect PIAB
  Allow Alarm Panel to place training call
  Confirm “normal” mode after next call
  Request alarm account to normal mode
Modem Line Cross-Connect
  Disconnect POTS – Connect PIAB
  Test modem equipment
Stage 1 – Install Prep
Stage 2 – Install TTU
Stage 3 – Cross-Connect

## Slide 3: High Level Best Practices
Project Coordination Lead​
  Each site should have a PM
  PM should ensure that they have local point of contact and “hand-hold” the process to ensure simple items like whether a device was delivered and store hours/access.
  PM should assist in the sales questionnaire/remote site survey
  PM can ask what circuits exist at site to decide if device should be primary WAN or LTE.
Bifurcate installs into Easy (1 visit) and Complex​ (1-2 visits)
  This can be by line type or number of lines or physical site.
  Others have done it by number of lines, if complex then usually two visits
  If you do two visits, use the first for survey and install and the second for porting/cross connect and close out of site
Provide techs with Device Management and/or local UI access ​
  This can cut down install times from 4hr+ to 1 hr as they don’t have to call tech support or 3rd party teams to change line types/modes
  Can troubleshoot on the fly
Port lines – eliminated need for third-party alarm vendor on site
  By porting the number ahead of time, no programming is required by the alarm tech.
  saves truck roll costs which are usually passed onto an already aggravated customer
Completing Install (on visit 1 or 2):
  Check signal strength
  Check line registration
  Complete cross connects
  Commence Post-Port Line Testing Procedures
  If applicable, Test Outbound on Alarms after Cross Connect but prior to porting

## Slide 4: Project Initiation
Designate PM – Each Site should have an install project manager
Identify Local Contact – Determine Local Contact Name, Email, Phone
Identify Availability - Determine local site business hours/availability for work
Determine Porting - Identify lines / telephone numbers to be ported
Identify NPA - Determine area code new TNs need to have (if applicable)
Verify shipping address - Ensure we know where to ship device for installation
Alarm Waiver – Obtain waiver for work to be performed with the alarm system
Technical Assessment
  WAN Uplink Capability (firewall considerations) - determine firewall/DNS requirements at the site
  Cellular Signal Assessment - determine expectation of cellular signal at the site
  Analog Devices on Site - determine what analog devices will need a POTS replacement connection

## Slide 5: Project Logistics
Enter porting order - Submit port order to bring over the phone number(s)
Establish VoIP Lines - Provision VoIP platform with SIP user accounts
Confirm E911 and CNAM - Populate call info on the SIP accounts
Activate SIM Card – Ensure cellular account is enabled
Provision device – Apply
Ship device to site
Confirm receipt of device on site

## Slide 6: Tools For The Technician
Sufficient quantity of dual RJ-45 port surface mount boxes (aka Biscuit Jack)
Sufficient quantity of RJ-11 or RJ-45 keystone plugs
Power strip (as a precaution in case there are not sufficient outlets in the room)
Extra RJ-11 cable and RJ-11 male adapters, in the event additional or longer runs are required
Cordless drill/driver with bits to install mounting hardware to wallboard
All hand tools required to make Cat5 cable runs (glow-stick, wire tape, etc.)
Butt Set (or analog test telephone if Butt Set doesn't have an RJ-11 plug/jack interface)
Camera with 3.0 megapixels or higher photo resolution (Modern cellphone will suffice)
All termination tools and line/tone testers
Zip Ties / Velcro for wire management
Cat5e patch cables of varying lengths
Label maker (to label biscuit jacks)
CAT5E cable – minimum 150 feet
6" torpedo level
Voltmeter
Flashlight

## Slide 7: Technician Skillset
Recommended Skillset for PIAB Installations
Basic familiarity with analog appliances, such as Fire Panel, Burglar Panels, Call Boxes, FAX machines, and modems.
Extensive experience with the connection of analog devices to POTS/Voice lines.
Extensive experience using a cable toner to identify twisted pair copper lines in a facility.
Extensive experience using a buttset and banjo for POTS line testing.
Experience installing and using telephone biscuit jacks as a termination point for phone line connections.
Basic networking experience for RJ-45 connections to a local area network and validating connectivity with a laptop.
Ability to locate DEMARC for existing POTS lines that provide dial tone to analog appliances, familiarity with 66-block/110-block terminations, and use of a punch-down tool to make cross connections.
Familiarity with DataRemote installation best practices for PIAB installations. Most notably, testing procedures for analog call validation, foreign voltage detection, and basic troubleshooting.
Experience with the physical mounting of networking equipment.
Experience using a multi-meter to check DC voltage and continuity.
Familiarity with troubleshooting techniques for local network issues (firewall, DNS, etc.).

## Slide 8: On-Site – Device Setup
Plug in PIAB Device
Connect WAN Uplink
  Confirm WAN Uplink link status
  Ping to 8.8.8.8 working Common Issue: Firewall blocking traffic
  DNS resolution working Potential Issue: DNS resolution issues
Confirm Cellular Internet Connectivity
  SIM Activated
  APN Details – if needed Potential Issue: SIM not activated
  Signal Strength Good Potential Issue: Cell signal not ideal

## Slide 9: On-Site – Inside Wiring
Identify Analog Lines at the Panel
Perform test call from panel end with banjo/butt set – confirm existing POTS line & trace to DMARC
Install Biscuit Jack next to PIAB Device
Check line for voltage on biscuit jack before plugging into DataRemote
Note – Cross-connect direct to 66/110-block is an option if technician has experience with punch-down and telephony connections. If not, then biscuit jack is recommended for simplicity and reducing risk of incorrect cross-connect.
Perform Alarm Test Call - Once the call has begun, dial tone should be heard, and then DTMF dialing tones should be heard. Shortly after, more tones will be heard corresponding to the alarm messages being sent via the configured protocol. When Alarm line is placed in AUTO detect mode, the first call will be a failed call. This is expected because the device is working with the panel to identify the protocol so that the configuration can be automatically updated. The second call is expected to be successful.
Perform FAX Line Test Call – It is important to note that a line configured for FAX mode does not carry voice audio. You can still use a buttset to perform a test call, but you will only be able to hear FAX handshake audio tones on the line. This is expected, and this test call allows you to confirm that the line can successfully make a phone call. Performing a real FAX call with a FAX machine is needed to confirm that the FAX can communicate successfully.

## Slide 10: Tier 2 – Considerations for Alarm Line Installs
A customer-signed Alarm Waiver is recommended
Use care when plugging a buttset into a port configured as Alarm-AUTO because the first call is used to automatically detect the alarm protocol. A detailed task plan for alarm line testing & validation is essential for high alarm install success rate.
Invoke a Fire Alarm Panel “trouble condition” by removing the telephone line connections for the alarm panel for at least 3 minutes. When plugging back in, the alarm panel will make a call home.
If the alarm mode has been changed from AUTO mode before successfully completing the setup, configure the line mode back to AUTO and perform an alarm test call.
Another method for triggering an alarm call is to disconnect the battery.

## Slide 11: Tier 2 – Considerations for FAX Line Installs
Ensure that FAX lines are configured in FAX Mode.
To increase the chance of FAX success we recommend configuring the fax machine to the following settings:
  Baud rate – 9600
  ECM - Off
NOTE: The printing duration per page can range from 25 seconds to 1 minute, contingent upon factors such as the BAUD rate, line quality, and signal quality.
When a phone line is configured in FAX mode, the line cannot be used to make voice calls. This is particularly important to understand when testing the line because if a technician connects a buttset to a FAX-configured line and makes a call, they will only hear FAX tones on both ends. No voice traffic will be carried in either direction. This is normal and expected.